## Overview
RACI Matrix for AI/ML & Automation Initiatives
Bank ABC - Innovation & Digitization Department
RACI Legend
Code | Meaning | Description
R | Responsible | Person who does the work to complete the task
A | Accountable | Person ultimately answerable for the completion and approval
C | Consulted | Person whose input is sought (two-way communication)
I | Informed | Person who is kept up-to-date on progress (one-way communication)
R/A | Responsible & Accountable | Person who both does the work and is accountable
Role Abbreviations
Abbreviation | Full Role | Description
BizSpon | Business Sponsor | Senior business leader sponsoring the initiative
BizOwn | Business Owner | Day-to-day business point of contact
DigProdHead | Head of Digital Products | Backlog management, requirements, UAT coordination
AILead | AI Engineering Lead | Head of AI Engineering team
BA | Business Analyst | Analyzes requirements, documents processes
DS | Data Scientist | Develops AI/ML models
MLE | ML Engineer | Implements ML pipelines, handles MLOps
AutoDev | Automation Developer | Develops RPA bots, automation solutions
SolArch | Solution Architect | Defines solution architecture
DataEng | Data Engineer | Builds data pipelines
ModelVal | Model Validator | Performs independent validation
QA | Quality Assurance | Tests and validates solutions
ItOps | IT Operations | Manages production infrastructure
ItSec | IT Security | Reviews security requirements
ItInfra | IT Infrastructure | Manages infrastructure
Comply | Compliance | Ensures regulatory compliance
Risk | Risk Management | Assesses and manages risks
EntArch | Enterprise Architecture | Oversees enterprise architecture
DataGov | Data Governance | Manages data governance
SteerCom | Steering Committee | Senior governance body for Tier 1 initiatives

## 3. Gate 0 - Intake
5. Gate 0: Intake & Prioritization RACI
5.1 Use Case Submission
Activity | BizSpon | BizOwn | DigProdHead | AILead | BA | SteerCom | Comply | Risk
Identify business problem/opportunity | A | R | C | I | I | I | I | I
Complete Use Case Intake Form | C | A | R | C | R | I | I | I
Define success metrics | A | R | R | C | C | I | I | I
Estimate business benefits | A | R | R | I | C | I | I | I
Identify stakeholders | R | R | R | C | C | I | I | I
5.2 Initial Screening
Activity | BizSpon | BizOwn | AILead | BA | DS | AutoDev | ItSec | Comply | Risk | EntArch | DataGov
Review intake submission | I | I | A | R | C | C | I | I | I | I | I
Assess strategic alignment | C | C | R/A | R | I | I | I | I | I | I | I
Assess technical feasibility (preliminary) | I | C | R | R | R | R | I | I | I | C | I
Identify data availability | I | C | R | R | R | I | I | I | I | I | C
Assess regulatory sensitivity | I | C | C | R | I | I | C | R | R | I | C
Assess security sensitivity | I | I | C | R | I | I | R | I | C | I | I
Determine risk tier (Tier 1/2/3) | I | I | A | R | I | I | C | C | R | I | I
Calculate prioritization score | I | C | A | R | I | I | I | I | I | I | I
5.3 Intake Decision
Activity | I I: BizSpon; I C: AILead; A A: BA; R R: SteerCom; I I: Comply; I I: Risk
Present to decision authority | I I: I; I C: R; A A: R; R R: I*; I I: I*; I I: I*
Make intake decision (Approve/Defer/Reject) | I I: I; I C: A**; A A: R; R R: A*; I I: I; I I: I
Communicate decision to stakeholders | I I: I; I C: A; A A: R; R R: I; I I: I; I I: I
Log decision and rationale | I I: I; I C: A; A A: R; R R: I; I I: I; I I: I
Update intake pipeline | I I: I; I C: A; A A: R; R R: I; I I: I; I I: I

## 4. Gate 1 - Discovery
6. Gate 1: Discovery & Feasibility RACI
6.1 Requirements Analysis
Activity | BizSpon | BizOwn | DigProdHead | AILead | BA | DS | AutoDev | DataEng | DataGov
Conduct requirements workshops | I | R | R | C | R/A | R | R | I | I
Document business requirements | I | R | R | C | R/A | C | C | I | I
Define functional requirements | I | R | R | C | R/A | R | R | I | I
Define non-functional requirements | I | C | C | R | R/A | R | R | C | I
Document as-is process (automation) | I | R | C | C | R/A | I | R | I | I
Identify exception scenarios | I | R | R | C | R/A | C | R | I | I
Volume and frequency analysis (automation) | I | R | C | C | R/A | I | R | I | I
6.2 Data Assessment
Activity | BizSpon | BizOwn | AILead | BA | DS | DataEng | ItSec | DataGov
Identify data sources | I | R | C | R | R | R | I | C
Assess data availability | I | C | C | R | R | R | I | C
Assess data quality | I | I | C | R | R | R | I | R
Evaluate data access requirements | I | C | C | R | R | R | R | R
Identify data gaps and remediation | I | C | R/A | R | R | R | I | C
Assess PII/sensitive data handling | I | I | C | R | C | I | R | R
Document data lineage | I | I | C | R | R | R | I | R
6.3 Technical Feasibility
Activity | BizSpon | AILead | BA | DS | MLE | AutoDev | SolArch | EntArch
Conduct proof of concept (if required) | I | R | C | R | R | R | C | I
Evaluate ML algorithms (AI initiatives) | I | R | I | R/A | R | I | C | I
Evaluate automation approach (RPA initiatives) | I | R | C | I | I | R/A | C | I
Assess technical risks | I | R/A | R | R | R | R | C | C
Identify technology dependencies | I | R | R | R | R | R | R | C
Estimate development effort | I | R/A | R | R | R | R | C | I
Recommend approach | I | R/A | R | R | R | R | C | C
6.4 Risk & Compliance Assessment
Activity | BizSpon | AILead | BA | ItSec | Comply | Risk | DataGov
Identify compliance requirements | I | C | R | C | R/A | C | C
Conduct regulatory impact assessment | C | C | R | I | R/A | R | C
Identify ethical considerations | C | C | R | I | R | R | C
Assess fairness and bias risks (AI) | I | C | R | I | C | R/A | C
Document risk mitigation approach | I | R | R | C | C | R/A | I
6.5 Feasibility Decision (Gate 1 Approval)
Activity | BizSpon | BizOwn | AILead | BA | SteerCom | Risk
Prepare feasibility report | I | C | R | R/A | I | I
Present to decision authority | C | C | R | R | I* | I*
Make feasibility decision (Go/No-Go) | C | C | A** | R | A* | C
Approve resource allocation | A | I | R | C | C* | I
Define project charter | I | C | R/A | R | I | I

## 5. Gate 2 - Design
7. Gate 2: Design Phase RACI
7.1 Solution Design (AI/ML Initiatives)
Activity | BizOwn | AILead | BA | DS | MLE | SolArch | DataEng | EntArch
Design overall solution architecture | I | R | C | R | R | R/A | C | C
Select ML algorithms and approach | I | R | C | R/A | R | C | I | I
Design feature engineering approach | I | C | C | R/A | R | I | C | I
Design model training strategy | I | R | C | R/A | R | C | I | I
Design explainability approach | C | R | C | R/A | R | C | I | I
Design data pipeline architecture | I | R | C | R | R | C | R/A | C
Define model performance targets | C | R | R | R/A | R | C | I | I
7.2 Solution Design (Automation Initiatives)
Activity | BizOwn | AILead | BA | AutoDev | SolArch | DataEng | EntArch
Design to-be process flow | R | C | R/A | R | C | I | I
Design automation architecture | C | R | R | R/A | R/A | C | C
Design exception handling approach | R | C | R | R/A | C | I | I
Design bot/flow components | I | C | C | R/A | C | I | I
Design orchestration and scheduling | I | R | R | R/A | C | I | I
Design integration approach | C | R | R | R/A | C | R | C
7.3 Integration & Infrastructure Design
Activity | AILead | BA | MLE | AutoDev | SolArch | DataEng | ItInfra | EntArch
Define integration requirements | C | R | R | R | R/A | R | C | C
Design API specifications | I | C | R | R | R/A | C | C | C
Define infrastructure requirements | C | C | R | R | R | C | R/A | C
Design deployment architecture | C | C | R | R | R/A | C | R | C
Plan environment strategy (dev/test/prod) | C | C | R | R | R | C | R/A | C
7.4 Security & Compliance Design
Activity | AILead | BA | MLE | AutoDev | ItSec | Comply | DataGov
Define security requirements | C | R | R | R | R/A | C | C
Design access controls | I | R | R | R | R/A | I | C
Design data protection measures | I | R | R | R | R/A | C | R
Design audit logging | I | R | R | R | R/A | C | C
Design compliance controls | C | R | C | C | C | R/A | C
7.5 Architecture Decision Records
Activity | AILead | MLE | AutoDev | SolArch | EntArch
Document architecture decisions (ADRs) | R | R | R | R/A | C
Review and approve ADRs | A | I | I | R | A**
Maintain ADR repository | R/A | I | I | R | I
7.6 Design Approval (Gate 2)
Activity | BizOwn | AILead | SolArch | SteerCom | Risk | EntArch
Prepare Solution Design Document | C | R | R/A | I | I | I
Review solution design | C | R | R | I* | C* | R
Approve solution design | C | A** | R | A* | I | C
Approve build phase resource plan | C | A | R | C* | I | I

## 6. Gate 3 - Build
8. Gate 3: Build Phase RACI
8.1 Environment Setup
Activity | AILead | DS | MLE | AutoDev | DataEng | ItInfra | ItSec
Provision development environment | C | I | R | R | C | R/A | C
Configure source control | R | R | R | R | I | C | C
Setup CI/CD pipeline | C | C | R/A | R | C | R | C
Provision test data | C | R | R | R | R/A | R | C
Configure secrets management | C | C | R | R | I | R | R/A
8.2 Data Preparation (AI/ML Initiatives)
Activity | AILead | DS | MLE | DataEng | DataGov
Build data extraction pipelines | C | R | R | R/A | I
Implement data quality checks | C | R | R | R | C
Perform data cleaning and preprocessing | C | R/A | R | R | I
Implement feature engineering | C | R/A | R | C | I
Create feature store (if applicable) | C | R | R/A | R | C
Document data transformations | C | R/A | R | R | C
8.3 Model Development (AI/ML Initiatives)
Activity | AILead | DS | MLE | BA
Develop model training code | C | R/A | R | I
Conduct model experiments | C | R/A | R | I
Perform hyperparameter tuning | C | R/A | R | I
Implement model explainability | C | R/A | R | C
Conduct bias and fairness testing | C | R/A | R | C
Select final model | R | R/A | R | C
Document Model Card | C | R/A | R | R
8.4 Automation Development (Automation Initiatives)
Activity | AILead | BA | AutoDev
Build bot/flow components | C | R | R/A
Implement exception handling | C | R | R/A
Implement logging and monitoring | R | R | R/A
Develop reusable components | C | C | R/A
Implement bot orchestration | C | R | R/A
Document bot/flow design | C | R/A | R
8.5 Code Quality & Testing
Activity | AILead | BA | DS | MLE | AutoDev | QA
Conduct code reviews | R | C | R | R | R | I
Write unit tests | C | C | R | R | R | C
Perform unit testing | C | R | R | R | R | R
Perform integration testing | C | R | R | R | R | R/A
Test exception handling | C | R | R | R | R | R
Fix defects | C | C | R | R | R | C
8.6 Documentation
Activity | AILead | BA | DS | MLE | AutoDev
Create technical documentation | C | R | R | R | R
Document code and components | C | C | R/A | R | R
Create user/operator guides | C | R/A | C | C | R
Update Solution Design Document | C | R/A | R | R | R
Prepare validation handoff package | R | R | R | R | R

## 7. Gate 4 - Validation
9. Gate 4: Validation & Testing RACI
9.1 Model Validation (AI/ML Initiatives)
Activity | BizOwn | AILead | DS | MLE | ModelVal | Risk
Conduct conceptual soundness review | I | C | C | C | R/A | C
Validate data quality | I | C | R | R | R/A | I
Validate model performance | I | C | R | R | R/A | C
Test model stability | I | C | R | R | R/A | I
Conduct sensitivity analysis | I | C | R | R | R/A | I
Validate bias and fairness | I | C | R | R | R/A | C
Benchmark against alternatives | I | C | R | R | R/A | I
Document limitations and assumptions | I | C | R | R | R/A | I
Prepare validation report | I | C | C | C | R/A | C
Sign-off validation | I | C | I | I | R | A
9.2 Automation Testing (Automation Initiatives)
Activity | BizOwn | AILead | BA | AutoDev | QA
Execute functional testing | C | C | R | R | R/A
Test exception scenarios | C | C | R | R | R/A
Perform volume testing | C | C | R | R | R/A
Test recovery procedures | I | C | R | R | R/A
Verify logging and monitoring | I | R | R | R | R
Peer validation (Tier 2) | I | R | R | R | A
9.3 User Acceptance Testing
Activity | BizOwn | DigProdHead | AILead | BA | QA
Prepare UAT plan and test cases | R | R | C | R/A | R
Coordinate UAT execution | R | R/A | C | R | R
Execute UAT test cases | R/A | R | I | R | R
Document UAT results | R | R | C | R/A | R
Sign-off UAT | A | R | I | R | C
9.4 Security & Compliance Testing
Activity | AILead | MLE | AutoDev | ItSec | Comply
Conduct security testing | C | R | R | R/A | I
Perform vulnerability scanning | C | C | C | R/A | I
Test access controls | C | R | R | R/A | I
Review compliance controls | C | C | C | C | R/A
Document security assessment | C | C | C | R/A | C
Sign-off security review | I | I | I | A | C
9.5 Validation Approval (Gate 3)
Activity | BizOwn | AILead | ModelVal | SteerCom | Risk | Comply
Review validation findings | R | R | R | I* | C | C
Address validation findings | C | R | C | I | I | I
Approve validation completion | C | A** | C | A* | C | C
Approve for production deployment | C | A** | I | A* | C | C

## 8. Gate 5 - Deployment
10. Gate 5: Deployment RACI
10.1 Pre-Deployment Preparation
Activity | BizOwn | AILead | MLE | AutoDev | ItInfra | ItOps
Prepare deployment runbook | I | R | R/A | R | C | C
Provision production infrastructure | I | C | R | R | R/A | C
Configure production environment | I | C | R | R | R | R/A
Conduct deployment rehearsal | I | R | R | R | C | R
Prepare rollback plan | I | R | R/A | R | C | R
Complete pre-deployment checklist | I | A | R | R | C | R
10.2 Deployment Execution
Activity | BizOwn | AILead | MLE | AutoDev | ItInfra | ItOps
Execute deployment | I | R | R/A | R | R | R
Configure monitoring and alerting | I | R | R | R | C | R/A
Conduct smoke testing | C | R | R | R | C | R
Verify integrations | C | R | R | R | R | R
Activate production monitoring | I | R | R | R | C | R/A
10.3 Cutover & Go-Live
Activity | BizOwn | AILead | MLE | AutoDev | ItOps
Coordinate cutover activities | R | R/A | R | R | R
Execute cutover plan | R | R | R | R | R
Verify production functionality | R/A | R | R | R | R
Provide hypercare support | R | R | R | R | R
Monitor initial production runs | R | R | R | R | R/A
10.4 Production Approval (Gate 4)
Activity | BizOwn | AILead | SteerCom | ItOps
Validate deployment success | R | R | I* | R
Approve production go-live | A | R** | A* | C
Sign-off production release | R | A | I | C

## 9. Post-Impl & Ops
11. Post-Implementation Review RACI
11.1 Benefits Realization (Gate 5)
Activity | BizSpon | BizOwn | DigProdHead | AILead | BA
Measure actual benefits vs. expected | C | R/A | R | C | R
Assess business impact | R | R/A | R | C | R
Document lessons learned | C | R | R | R/A | R
Identify improvement opportunities | C | R | R | R | R
11.2 Technical Performance Review
Activity | BizOwn | AILead | DS | MLE | AutoDev | ItOps
Review model/bot performance metrics | C | R/A | R | R | R | R
Assess technical stability | I | R/A | R | R | R | R
Review incident history | I | R/A | C | C | C | R
Identify technical improvements | I | R/A | R | R | R | R
11.3 PIR Approval
Activity | BizSpon | BizOwn | DigProdHead | AILead | SteerCom
Prepare PIR report | C | R | R | R/A | I
Present PIR findings | C | R | R | R | I*
Approve PIR closure | C | R | R | A** | A*
12. Ongoing Operations & Maintenance RACI
12.1 Production Monitoring
Activity | BizOwn | AILead | DS | MLE | AutoDev | ItOps
Monitor model/bot performance | C | R | R | R | R | R/A
Monitor data drift (AI/ML) | I | R | R/A | R | I | C
Monitor prediction quality (AI/ML) | C | R | R/A | R | I | C
Monitor bot execution (Automation) | C | R | C | I | R | R/A
Monitor system health | I | R | C | C | C | R/A
Review monitoring dashboards | C | R | R | R | R | R
Respond to monitoring alerts | I | R | R | R | R | R/A
12.2 Incident Management
Activity | BizOwn | AILead | DS | MLE | AutoDev | ItOps
Respond to production incidents | C | R | R | R | R | R/A
Investigate root cause | I | R | R | R | R | R
Implement fixes | I | R | R | R | R | R
Document incidents and resolutions | I | R | R | R | R | R/A
Conduct incident post-mortems | C | R/A | R | R | R | R
12.3 Maintenance & Support
Activity | BizOwn | AILead | DS | MLE | AutoDev | ItOps
Perform routine maintenance | I | R | R | R | R | R/A
Apply patches and updates | I | R | R | R | R | R
Update documentation | I | R | R | R | R | C
Provide user support | R | C | C | C | C | C
Handle change requests | R | R | C | C | C | C
12.4 Performance Reporting
Activity | BizSpon | BizOwn | AILead | BA | SteerCom
Generate performance reports | I | C | R | R/A | I
Analyze performance trends | I | R | R | R | I
Report to business stakeholders | I | R/A | R | R | I
Report to Steering Committee (Tier 1) | C | C | R | R | I
12.5 Periodic Reviews
Activity | BizOwn | AILead | DS | MLE | AutoDev | ModelVal | Risk
Conduct quarterly reviews (Tier 1) | R | R/A | R | R | R | C | C
Conduct semi-annual reviews (Tier 2) | R | R/A | R | R | R | C | I
Conduct annual reviews (Tier 3) | R | R/A | R | R | R | I | I
Assess continued appropriateness | R | R | R | R | R | C | C
Recommend retraining/updates | C | R | R/A | R | R | I | I
Update model inventory | I | R | C | C | C | I | I

## 10. Retraining & Retire
13. Retraining & Enhancement RACI
13.1 Retraining Trigger Assessment (AI/ML)
Activity | BizOwn | AILead | DS | MLE | ModelVal
Identify retraining triggers | C | R | R/A | R | I
Assess performance degradation | C | R | R/A | R | C
Evaluate new data availability | I | R | R/A | R | I
Recommend retraining approach | I | R | R/A | R | C
Approve retraining initiation | C | A | R | R | I
13.2 Bot/Flow Enhancement (Automation)
Activity | BizOwn | AILead | BA | AutoDev
Identify enhancement needs | R | C | R | C
Assess process changes | R/A | C | R | C
Design enhancements | C | R | R | R/A
Approve enhancement scope | A | R | R | C
13.3 Retraining/Enhancement Execution
Activity | AILead | DS | MLE | AutoDev | ModelVal
Execute retraining/enhancement | R | R/A | R | R | I
Validate retrained model/updated bot | C | R | R | R | R/A
Conduct regression testing | R | R | R | R | C
Approve for production | A | C | C | C | C**
Deploy to production | R | R | R | R | I
14. Model/Bot Retirement RACI
14.1 Retirement Assessment
Activity | BizSpon | BizOwn | AILead | DS | AutoDev | Risk
Identify retirement candidates | C | R | R/A | R | R | I
Assess business impact of retirement | R | R/A | C | I | I | I
Assess technical dependencies | I | C | R | R | R | C
Evaluate replacement options | C | R | R | R | R | I
Recommend retirement decision | I | R | R/A | R | R | C
14.2 Retirement Planning
Activity | BizOwn | AILead | MLE | AutoDev | ItOps
Develop retirement plan | C | R | R | R | R
Plan data archival | C | R | R | R | C
Plan system decommissioning | I | R | R | R | R/A
Coordinate with dependent systems | R | R | R | R | R
Prepare stakeholder communications | R/A | R | I | I | I
14.3 Retirement Execution
Activity | BizOwn | AILead | MLE | AutoDev | ItOps
Execute retirement plan | C | R | R | R | R/A
Archive model/bot artifacts | I | R | R | R | R
Archive data and documentation | I | R | R | R | R
Deactivate production systems | I | R | R | R | R/A
Update model inventory | I | R/A | C | C | I
Communicate retirement completion | R | R/A | I | I | I
14.4 Retirement Approval
Activity | BizSpon | BizOwn | AILead | SteerCom
Approve retirement decision | C | A | R | C*
Sign-off retirement completion | C | R | A | I

## 11. Copilot Mgmt
15. Copilot Tools Management RACI
15.1 Copilot Provisioning & Licensing
Activity | DigProdHead | AILead | BA | ItInfra | ItSec | Comply | BizSpon
Define Copilot licensing strategy | R | R | C | C | C | C | A
Request Copilot licenses (O365, etc.) | R | C | R | R | I | I | A
Provision user licenses | I | C | R | R/A | C | I | I
Configure tenant settings | I | R | C | R/A | R | C | I
Define user eligibility criteria | R | R | R | I | C | R | A
Manage license allocation | R/A | C | R | R | I | I | C
Track license utilization | R/A | C | R | R | I | I | C
Optimize license costs | R/A | C | R | R | I | I | A
15.2 Copilot Governance & Policy Management
Activity | DigProdHead | AILead | ItSec | Comply | DataGov | BizSpon
Define Copilot usage policies | R | R/A | R | R | R | C
Configure data protection policies | C | R | R/A | R | R | I
Define acceptable use guidelines | R | R | C | R | C | C
Configure prompt controls | C | R/A | R | C | C | I
Manage data residency settings | I | R | R | R | R/A | I
Define sensitive data handling rules | C | R | R | R | R/A | C
Review and update policies | R | R/A | R | R | R | C
Enforce policy compliance | R | R/A | R | R | C | I
15.3 Copilot User Training & Enablement
Activity | DigProdHead | AILead | BA | BizOwn | ItInfra
Develop Copilot training materials | R/A | R | R | C | I
Create usage guidelines and best practices | R/A | R | R | C | I
Conduct user onboarding sessions | R/A | C | R | C | C
Provide prompt engineering training | R | R/A | R | C | I
Develop use case examples | R/A | R | R | R | I
Create FAQ and help documentation | R/A | C | R | C | I
Conduct train-the-trainer sessions | R/A | C | R | C | I
Measure training effectiveness | R/A | C | R | C | I
15.4 Copilot Usage Monitoring & Analytics
Activity | DigProdHead | AILead | BA | ItSec | Comply | DataGov
Monitor usage patterns and adoption | R/A | R | R | C | I | I
Track prompt quality and effectiveness | R | R/A | R | I | I | I
Analyze user engagement metrics | R/A | C | R | I | I | I
Monitor for policy violations | R | R | C | R | R | C
Review sensitive data exposure risks | C | R | C | R/A | R | R
Generate usage reports and dashboards | R/A | C | R | C | I | I
Identify optimization opportunities | R/A | R | R | I | I | I
Report usage metrics to leadership | R/A | C | R | I | I | I
15.5 Copilot Support & Issue Resolution
Activity | DigProdHead | AILead | BA | ItInfra | ItSec
Provide first-line user support | R/A | C | R | C | I
Troubleshoot technical issues | C | R | R | R/A | C
Escalate to Microsoft support | C | R | R | R/A | I
Manage incident tickets | R | C | R | R | I
Document known issues and workarounds | R | R | R/A | C | I
Coordinate with IT for infrastructure issues | R | R/A | C | R | C
Communicate service disruptions | R/A | C | R | R | I
Track and resolve user feedback | R/A | C | R | I | I
15.6 Copilot Performance & Cost Management
Activity | DigProdHead | AILead | BA | ItInfra | BizSpon
Monitor Copilot performance metrics | R | R/A | R | R | I
Track API usage and throttling | C | R/A | C | R | I
Analyze cost vs. value metrics | R/A | C | R | I | C
Optimize token consumption | C | R/A | R | R | I
Review service health and availability | R | R/A | C | R | I
Benchmark against industry standards | R/A | R | C | I | C
Conduct ROI analysis | R/A | C | R | I | A
Recommend service improvements | R/A | R | R | C | C

## 12. Hub Mgmt
16. AI & Automation Hub Management RACI
16.1 Hub Platform Management
Activity | DigProdHead | AILead | BA | ItInfra | EntArch
Define Hub vision and roadmap | R | R/A | C | C | C
Design Hub architecture and features | C | R/A | R | R | R
Develop and maintain Hub platform | R | R/A | R | R | C
Configure Hub access controls | C | R | R | R/A | C
Manage Hub infrastructure | I | R | C | R/A | C
Deploy Hub updates and enhancements | C | R/A | R | R | C
Monitor Hub performance and availability | R | R/A | R | R | I
Ensure Hub security and compliance | C | R | C | R | R
16.2 Hub Content & Catalog Management
Activity | DigProdHead | AILead | BA | DS | AutoDev
Curate AI/Automation solution catalog | R/A | R | R | C | C
Document available models and bots | C | R | R/A | R | R
Maintain use case library | R/A | R | R | C | C
Publish best practices and guidelines | R | R/A | R | C | C
Create solution templates and accelerators | C | R | R/A | R | R
Manage Hub taxonomy and metadata | R/A | R | R | C | C
Update model/bot documentation | C | R | R | R | R
Retire outdated content | R | R/A | R | C | C
16.3 Hub User Access & Onboarding
Activity | DigProdHead | AILead | BA | ItSec | BizOwn
Define Hub user roles and permissions | R | R/A | R | R | C
Manage user access requests | R/A | C | R | R | C
Onboard new Hub users | R/A | C | R | I | C
Provide Hub orientation training | R/A | C | R | I | C
Create user guides and tutorials | R/A | R | R | I | C
Manage user directories and profiles | R | C | R | R | I
Review and audit user access | R | R | R | R/A | I
Deactivate user access when needed | R | C | R | R/A | I
16.4 Hub Usage Analytics & Reporting
Activity | DigProdHead | AILead | BA | BizSpon | SteerCom
Track Hub usage and adoption metrics | R/A | R | R | I | I
Monitor most accessed solutions | R/A | R | R | I | I
Analyze user engagement patterns | R/A | C | R | I | I
Generate Hub analytics reports | R/A | C | R | I | I
Measure Hub value and ROI | R/A | R | R | C | I
Identify content gaps and needs | R/A | R | R | C | I
Report Hub metrics to leadership | R/A | C | R | C | I*
Benchmark Hub performance | R/A | R | C | C | I
16.5 Hub Support & Community Management
Activity | DigProdHead | AILead | BA | BizOwn
Provide Hub user support | R/A | C | R | C
Manage Hub support tickets | R/A | C | R | I
Facilitate Hub user community | R/A | R | R | C
Organize Hub user forums and events | R/A | C | R | C
Collect and prioritize user feedback | R/A | R | R | R
Coordinate knowledge sharing sessions | R/A | R | R | C
Maintain Hub FAQ and help resources | R/A | C | R | C
Recognize and promote Hub champions | R/A | C | C | C
16.6 Hub Integration & Ecosystem Management
Activity | DigProdHead | AILead | SolArch | ItInfra | EntArch
Define Hub integration strategy | R | R/A | R | C | R
Integrate Hub with enterprise systems | C | R | R/A | R | R
Manage Hub API and SDKs | C | R/A | R | R | C
Coordinate with IT on infrastructure | R | R/A | C | R | R
Manage third-party tool integrations | R | R/A | R | R | C
Ensure Hub interoperability | C | R | R/A | R | R
Maintain Hub integration documentation | R | R | R/A | C | C
Evaluate new integration opportunities | R/A | R | R | C | C
16.7 Hub Governance & Compliance
Activity | DigProdHead | AILead | ItSec | Comply | DataGov
Define Hub governance policies | R | R/A | R | R | R
Ensure Hub regulatory compliance | C | R | R | R/A | R
Conduct Hub security assessments | C | R | R/A | C | C
Manage Hub data privacy controls | C | R | R | R | R/A
Audit Hub access and usage | R | R | R | R | C
Review and update Hub policies | R | R/A | R | R | R
Report Hub compliance status | R | R | C | R/A | C
Manage Hub risk register | C | R/A | C | R | C

## 13. Variations
17. Initiative Type Variations
18. Tier-Based Variations
18.4 Tier-Specific RACI Adjustments
Activity | Tier 1 | Tier 2 | Tier 3
Gate Approvals | SteerCom (A) | AILead (A) | AILead (A), can delegate
Model Validation | ModelVal Independent (R/A) | ModelVal Peer (R/A) | Team Self + Peer (R/A)
Risk Consultation | Risk (C) at all gates | Risk (C) at Gates 1, 3 | Risk (I) only
Compliance Review | Comply (C) at all gates | Comply (C) at Gates 1, 4 | Comply (I) only
Documentation | Comprehensive (all) | Standard (all) | Abbreviated (key only)
Periodic Reviews | Quarterly | Semi-annual | Annual

## 14. Appendices
20. Appendices
Appendix A: Quick Reference - Gate Approval Matrix
Gate | Tier 1 Approval | Tier 2 Approval | Tier 3 Approval
Gate 0: Intake | Steering Committee | AI Engineering Lead | AI Engineering Lead
Gate 1: Feasibility | AI Engineering Lead + Risk | AI Engineering Lead | AI Engineering Lead
Gate 2: Design | Steering Committee | AI Engineering Lead | AI Engineering Lead (delegable)
Gate 3: Validation | Steering Committee + Independent Validation | AI Engineering Lead + Peer Validation | AI Engineering Lead + Self-Validation
Gate 4: Production | Steering Committee | AI Engineering Lead | AI Engineering Lead (delegable)
Gate 5: PIR | Steering Committee | AI Engineering Lead | AI Engineering Lead
Appendix B: Quick Reference - Primary Responsible Parties by Phase
Phase | AI/ML Primary | Automation Primary | Product Management
Intake | Business Analyst | Business Analyst | Head of Digital Products
Discovery | Data Scientist + Business Analyst | Business Analyst + Business Owner | Head of Digital Products (requirements)
Design | Data Scientist + ML Engineer + Solution Architect | Automation Developer + Business Analyst + Solution Architect | Head of Digital Products (requirements approval)
Build | Data Scientist + ML Engineer | Automation Developer + Business Analyst | Head of Digital Products (stakeholder mgmt)
Validation | Model Validator + Data Scientist | QA + Automation Developer | Head of Digital Products (UAT coordination)
Deployment | ML Engineer + IT Operations | Automation Developer + IT Operations | Head of Digital Products (stakeholder comms)
Operations | ML Engineer + IT Operations + Data Scientist | Automation Developer + IT Operations | Head of Digital Products (benefits tracking)
Appendix C: Escalation Paths
Issue Level | Escalation Path
**Level 1**: Task/activity level | Team lead (DS/MLE/AutoDev)
**Level 2**: Phase/gate level | AI Engineering Lead
**Level 3**: Initiative level | Business Sponsor + AI Engineering Lead
**Level 4**: Portfolio/strategic | Steering Committee
**Level 5**: Enterprise impact | Executive Management