# AI & Automation Initiative Approval & Stage-Gate Process

Document ID: AI-GOV-003
Version: 1.1
Classification: Internal
Owner: Head of AI Engineering, Innovation & Digitization Department
Last Review Date: [Date]
Next Review Date: [Date + 12 months]

──────────────────────────────────────────────────

## 1. Executive Summary

### 1.1 Purpose

This document establishes the stage-gate process for AI, Automation, and Intelligent Solutions initiatives at Bank ABC. It provides a structured framework for progressing use cases from approved intake through production deployment and ongoing operations. It defines the gates, approval criteria, required artifacts, and governance controls at each stage of the initiative lifecycle.

### 1.2 Objectives

Ensure appropriate governance checkpoints throughout the initiative lifecycle

Define clear criteria for progression between stages

Scale governance intensity based on risk tier

Enable consistent quality and compliance across all AI and Automation initiatives

Support full lifecycle governance including retraining, bot updates, and periodic reviews

Maintain agility while ensuring appropriate controls

Coordinate effectively with IT Department for data and infrastructure needs

### 1.3 Scope

This process applies to:
- All AI/ML initiatives: Analytical AI, GenAI, and Agentic AI
- All Automation initiatives: RPA, Workflow Automation, Business Process Automation
- Hybrid initiatives combining AI and Automation
- Model retraining and bot/flow updates
- Periodic reviews and revalidations
- Retirement decisions

### 1.4 Organizational Context

Owning Department: Innovation & Digitization Department

Primary Approval Authority: Head of AI Engineering

Escalation: AI & Automation Steering Committee (Tier 1)

IT Coordination: IT Department (Data, Infrastructure, Security)

──────────────────────────────────────────────────

## 2. Stage-Gate Overview

### 2.1 Lifecycle Stages and Gates

┌──────────────────────────────────────────────────────────────────────────────────────────────────────────────────┐
│                                        AI/ML INITIATIVE LIFECYCLE                                                │
├──────────────────────────────────────────────────────────────────────────────────────────────────────────────────┤
│                                                                                                                  │
│  ┌─────────┐      ┌─────────┐      ┌─────────┐      ┌─────────┐      ┌─────────┐      ┌─────────┐              │
│  │ GATE 0  │      │ GATE 1  │      │ GATE 2  │      │ GATE 3  │      │ GATE 4  │      │ GATE 5  │              │
│  │ INTAKE  │      │FEASIBIL.│      │ DESIGN  │      │VALIDATION│     │PRODUCTION│     │  PIR    │              │
│  └────┬────┘      └────┬────┘      └────┬────┘      └────┬────┘      └────┬────┘      └────┬────┘              │
│       │                │                │                │                │                │                    │
│       ▼                ▼                ▼                ▼                ▼                ▼                    │
│  ┌─────────┐      ┌─────────┐      ┌─────────┐      ┌─────────┐      ┌─────────┐      ┌─────────┐              │
│  │DISCOVERY│ ───▶ │ DESIGN  │ ───▶ │  BUILD  │ ───▶ │VALIDATE │ ───▶ │ DEPLOY  │ ───▶ │ OPERATE │ ◀─┐         │
│  │         │      │         │      │         │      │         │      │         │      │         │   │         │
│  └─────────┘      └─────────┘      └─────────┘      └─────────┘      └─────────┘      └─────────┘   │         │
│                                                                                              │       │         │
│                                                                                              │  RETRAIN/       │
│                                                                                              │  ENHANCE        │
│                                                                                              │       │         │
│                                                                                              └───────┘         │
│                                                                                                                  │
│  ┌──────────────────────────────────────────────────────────────────────────────────────────────────────────┐  │
│  │                                    ONGOING GOVERNANCE                                                     │  │
│  │   • Performance Monitoring    • Periodic Reviews    • Retraining Gates    • Retirement Decision          │  │
│  └──────────────────────────────────────────────────────────────────────────────────────────────────────────┘  │
└──────────────────────────────────────────────────────────────────────────────────────────────────────────────────┘

### 2.2 Stage Definitions

| Stage | Purpose | Key Activities | Duration Target |
| --- | --- | --- | --- |
| Discovery | Validate feasibility and refine requirements | Data assessment, technical PoC, requirements refinement | 2-4 weeks |
| Design | Define solution architecture and approach | Solution design, architecture decisions, resource planning | 2-3 weeks |
| Build | Develop and test the model | Model development, feature engineering, testing | 4-12 weeks |
| Validate | Independent validation and UAT | Model validation, business testing, compliance review | 2-4 weeks |
| Deploy | Production deployment | Deployment execution, cutover, hypercare | 1-2 weeks |
| Operate | Ongoing production operations | Monitoring, maintenance, periodic review | Ongoing |

### 2.3 Gate Definitions

| Gate | Name | Purpose | Key Decision |
| --- | --- | --- | --- |
| Gate 0 | Intake Approval | Approve use case for discovery | Proceed to Discovery? |
| Gate 1 | Feasibility Sign-off | Confirm feasibility and proceed to design | Is this feasible and worth pursuing? |
| Gate 2 | Design Approval | Approve solution design for build | Is the design sound and ready for build? |
| Gate 3 | Validation Approval | Approve for production deployment | Does the model meet all requirements? |
| Gate 4 | Production Approval | Authorize production go-live | Is the model ready for production? |
| Gate 5 | Post-Implementation Review | Assess deployment success | Was the deployment successful? |

──────────────────────────────────────────────────

## 3. Governance Intensity by Risk Tier

### 3.1 Tier-Based Gate Requirements

| Gate | Tier 1 (High Risk) | Tier 2 (Medium Risk) | Tier 3 (Low Risk) |
| --- | --- | --- | --- |
| Gate 0 | AI & Automation Steering Committee | Head of AI Engineering | Head of AI Engineering |
| Gate 1 | Head of AI Engineering + Risk | Head of AI Engineering | Head of AI Engineering |
| Gate 2 | AI & Automation Steering Committee | Head of AI Engineering | Head of AI Engineering (delegated) |
| Gate 3 | AI & Automation Steering Committee + Independent Validation | Head of AI Engineering + Peer Validation | Head of AI Engineering + Self-Validation |
| Gate 4 | AI & Automation Steering Committee | Head of AI Engineering | Head of AI Engineering (delegated) |
| Gate 5 | AI & Automation Steering Committee | Head of AI Engineering | Head of AI Engineering |

### 3.2 Documentation Requirements by Tier

| Artifact | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- |
| Use Case Intake Form | Full | Full | Simplified |
| Feasibility Assessment | Comprehensive | Standard | Brief |
| Solution Design Document | Comprehensive | Standard | Abbreviated |
| Architecture Decision Records | All decisions | Significant decisions | Non-standard only |
| Model Card | Comprehensive | Standard | Brief |
| Validation Report | Independent, comprehensive | Peer review, standard | Self-assessment |
| Deployment Runbook | Comprehensive | Standard | Abbreviated |
| Monitoring Configuration | Comprehensive | Standard | Standard |

### 3.3 Fast-Track Process (Tier 3 Only)

Tier 3 initiatives may use a consolidated gate process:

┌─────────┐      ┌─────────────────┐      ┌─────────────────┐      ┌─────────┐
│ GATE 0  │ ───▶ │ GATE 1+2        │ ───▶ │ GATE 3+4        │ ───▶ │ GATE 5  │
│ INTAKE  │      │ FEASIBILITY +   │      │ VALIDATION +    │      │  PIR    │
│         │      │ DESIGN          │      │ PRODUCTION      │      │         │
└─────────┘      └─────────────────┘      └─────────────────┘      └─────────┘

──────────────────────────────────────────────────

## 4. Gate 0: Intake Approval

### 4.1 Entry Criteria

Use case intake form submitted

Business sponsor identified

Initial screening completed

### 4.2 Gate Activities

Intake assessment as per AI Use Case Intake & Prioritization Framework

Risk tier classification

Prioritization scoring

Resource availability check

### 4.3 Required Artifacts

| Artifact | Description | Owner |
| --- | --- | --- |
| Use Case Intake Form | Completed submission | Business Requestor |
| Screening Checklist | Initial screening results | AI Engineering |
| Prioritization Score | Assessment scoring | AI Engineering |
| Risk Tier Classification | Preliminary risk tier | AI Engineering |

### 4.4 Exit Criteria / Gate Checklist

| Criterion | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- |
| Intake form complete | ✓ | ✓ | ✓ |
| Business sponsor confirmed | ✓ | ✓ | ✓ |
| Strategic alignment validated | ✓ | ✓ | ✓ |
| Preliminary risk tier assigned | ✓ | ✓ | ✓ |
| Resource capacity confirmed | ✓ | ✓ | ✓ |
| AI Steering Committee approval | ✓ | - | - |

### 4.5 Approval Authority

Tier 1: AI Steering Committee

Tier 2/3: AI Engineering Lead

### 4.6 Outcomes

Approved: Proceed to Discovery; assign AI Engineering resources

Deferred: Add to backlog with rationale

Rejected: Archive with documented rationale

──────────────────────────────────────────────────

## 5. Gate 1: Feasibility Sign-off

### 5.1 Entry Criteria

Gate 0 approval received

Discovery phase initiated

AI Engineering team assigned

### 5.2 Discovery Phase Activities

| Activity | Description | Owner |
| --- | --- | --- |
| Data Assessment | Evaluate data availability, quality, accessibility | IT Data Management (coordination) |
| Technical Feasibility (AI) | Assess AI approach viability; PoC if needed | Data Scientist |
| Technical Feasibility (Automation) | Assess automation approach; process walkthrough | Business Analyst |
| Requirements Refinement | Clarify and document detailed requirements | Digital Product Owner + Business |
| Risk Assessment Update | Refine risk tier based on discovery findings | Head of AI Engineering |
| Effort Estimation | Detailed estimate for design and build | Data Scientist / Business Analyst |
| Stakeholder Alignment | Confirm stakeholder expectations | Business Sponsor |
| IT Coordination | Confirm data access, infrastructure needs | Head of AI Engineering + IT |

### 5.2.1 Automation-Specific Discovery Activities

| Activity | Description | Owner |
| --- | --- | --- |
| Process Documentation | Document as-is process with variations | Business Analyst |
| Process Walkthrough | Observe current manual process execution | Business Analyst |
| Exception Identification | Catalog all exception scenarios | Business Analyst |
| System Access Assessment | Identify system credentials and access requirements | Business Analyst + IT |
| Volume Analysis | Analyze transaction volumes and patterns | Business Analyst |
| Bot Architecture Assessment | Define attended/unattended, scheduling | Business Analyst |

### 5.3 GenAI-Specific Discovery Activities

| Activity | Description |
| --- | --- |
| Foundation Model Evaluation | Test candidate models against requirements |
| Prompt Engineering Assessment | Evaluate prompt complexity and approach |
| RAG Feasibility | Assess knowledge base and retrieval requirements |
| Output Quality Assessment | Evaluate output quality, hallucination risk |
| Guardrail Requirements | Define content filtering and safety requirements |

### 5.4 Agentic AI-Specific Discovery Activities

| Activity | Description |
| --- | --- |
| Autonomy Level Validation | Confirm appropriate autonomy level |
| Tool/API Assessment | Evaluate required integrations |
| Boundary Definition | Define and validate action boundaries |
| Human Oversight Design | Design intervention mechanisms |
| Risk Scenario Analysis | Analyze potential failure modes |

### 5.5 Required Artifacts

| Artifact | Description | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- | --- |
| Feasibility Assessment Report | Findings from discovery phase | Comprehensive | Standard | Brief |
| Data Assessment Report | Data availability, quality, gaps | ✓ | ✓ | ✓ |
| Technical PoC Results | PoC outcomes (if conducted) | Required | Recommended | Optional |
| Updated Risk Assessment | Refined risk tier and factors | ✓ | ✓ | ✓ |
| Effort Estimate | Resource and timeline estimate | Detailed | Detailed | High-level |
| Go/No-Go Recommendation | AI Engineering recommendation | ✓ | ✓ | ✓ |

### 5.6 Exit Criteria / Gate Checklist

| Criterion | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- |
| Data availability confirmed | ✓ | ✓ | ✓ |
| Technical feasibility confirmed | ✓ | ✓ | ✓ |
| Requirements documented | ✓ | ✓ | ✓ |
| Risk tier confirmed/updated | ✓ | ✓ | ✓ |
| Effort estimate accepted by sponsor | ✓ | ✓ | ✓ |
| PoC demonstrates viability | ✓ | Recommended | - |
| Risk/Compliance review complete | ✓ | ✓ | - |

### 5.7 Approval Authority

Tier 1: AI Engineering Lead + Risk Representative

Tier 2/3: AI Engineering Lead

### 5.8 Outcomes

Approved: Proceed to Design

Approved with Conditions: Proceed with specific conditions to address

Pivot: Revise approach and re-assess

Rejected: Feasibility concerns prevent progression; archive

──────────────────────────────────────────────────

## 6. Gate 2: Design Approval

### 6.1 Entry Criteria

Gate 1 approval received

Design phase initiated

Solution Architect assigned

### 6.2 Design Phase Activities

| Activity | Description | Owner |
| --- | --- | --- |
| Solution Architecture Design | Define end-to-end solution architecture | Head of AI Engineering (or delegate) |
| Model Approach Design (AI) | Define model type, features, training approach | Data Scientist |
| Automation Design (RPA/Workflow) | Define bot/flow architecture, exception handling | Business Analyst |
| Data Pipeline Design | Design data flows, feature engineering | Data Scientist + IT Data |
| Integration Design | Define integration points and patterns | Head of AI Engineering + IT |
| Infrastructure Design | Define compute, storage, deployment infrastructure | Head of AI Engineering + IT |
| Security Design | Security controls and threat assessment | IT InfoSec + I&D |
| Monitoring Design | Define monitoring approach and metrics | Head of AI Engineering |
| Architecture Decisions | Document key decisions as ADRs | Head of AI Engineering |

### 6.2.1 Automation-Specific Design Activities

| Activity | Description | Owner |
| --- | --- | --- |
| Bot/Flow Design | Detailed automation logic and flow design | Business Analyst |
| Exception Handling Design | Design exception workflows and escalation | Business Analyst |
| Credential Management Design | Define secure credential storage approach | Business Analyst + IT |
| Scheduling Design | Define run schedules and triggers | Business Analyst |
| Logging and Audit Design | Define transaction logging requirements | Business Analyst |

### 6.3 Required Artifacts

| Artifact | Description | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- | --- |
| Solution Design Document | Comprehensive solution documentation | Full | Standard | Abbreviated |
| Architecture Diagrams | High-level and component diagrams | ✓ | ✓ | ✓ |
| Architecture Decision Records | Key decision documentation | All | Significant | Non-standard |
| Data Flow Diagrams | Data lineage and flow | ✓ | ✓ | ✓ |
| Security Assessment | Threat model and controls | Full | Standard | Checklist |
| Infrastructure Specifications | Resource requirements | ✓ | ✓ | ✓ |
| Integration Specifications | API and integration design | ✓ | ✓ | If applicable |
| Monitoring Specifications | Metrics and alerting design | ✓ | ✓ | Standard |
| Test Strategy | Testing approach and coverage | ✓ | ✓ | ✓ |
| Project Plan | Build phase plan and resources | ✓ | ✓ | High-level |

### 6.4 GenAI-Specific Design Artifacts

| Artifact | Description |
| --- | --- |
| Foundation Model Selection ADR | Rationale for model selection |
| Prompt Architecture | System prompts, prompt templates, chaining |
| RAG Architecture | Vector store, embedding, retrieval design |
| Guardrail Specifications | Content filtering, output controls |
| Human Review Workflow | Review process design (if applicable) |

### 6.5 Agentic AI-Specific Design Artifacts

| Artifact | Description |
| --- | --- |
| Autonomy Level Specification | Detailed autonomy boundaries |
| Agent Action Catalog | All actions agent can perform |
| Tool Integration Design | API access and permissions |
| Orchestration Design | Multi-agent interaction (if applicable) |
| Human Override Design | Intervention mechanisms |
| Boundary Enforcement Design | Technical controls for limits |

### 6.6 Exit Criteria / Gate Checklist

| Criterion | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- |
| Solution Design Document complete | ✓ | ✓ | ✓ |
| Architecture aligned with standards | ✓ | ✓ | ✓ |
| Security assessment complete | ✓ | ✓ | Checklist |
| Data governance requirements addressed | ✓ | ✓ | ✓ |
| Infrastructure provisioning approved | ✓ | ✓ | ✓ |
| Build plan and resources confirmed | ✓ | ✓ | ✓ |
| Architecture Review Board sign-off | ✓ | If non-standard | - |
| Risk/Compliance design review | ✓ | ✓ | - |

### 6.7 Approval Authority

Tier 1: AI Steering Committee

Tier 2: AI Engineering Lead

Tier 3: AI Engineering Lead (may delegate)

### 6.8 Outcomes

Approved: Proceed to Build

Approved with Conditions: Proceed with specific design conditions

Revise: Significant design concerns require rework

Rejected: Design fundamentally flawed; return to Discovery or archive

──────────────────────────────────────────────────

## 7. Build Phase (No Gate)

### 7.1 Purpose

The Build phase executes the approved design. There is no formal gate at the end of Build; the phase transitions directly to Validation.

### 7.2 Build Phase Activities

AI Initiatives:

| Activity | Description | Owner |
| --- | --- | --- |
| Environment Setup | Provision development and test environments | Head of AI Engineering + IT |
| Data Pipeline Implementation | Build data ingestion and feature pipelines | Data Scientist |
| Feature Engineering | Implement feature transformations | Data Scientist |
| Model Development | Train and tune models | Data Scientist |
| Model Testing | Unit, integration, and performance testing | Data Scientist |
| Code Review | Peer review of all code | Head of AI Engineering |
| Documentation | Model card, technical documentation | Data Scientist |
| UAT Preparation | Prepare for business testing | Digital Product Owner + Business |

Automation Initiatives:

| Activity | Description | Owner |
| --- | --- | --- |
| Environment Setup | Configure development and test environments | Business Analyst + IT |
| Bot/Flow Development | Build automation logic | Business Analyst (or Automation Developer when hired) |
| Exception Handling Implementation | Build exception workflows | Business Analyst |
| Integration Development | Build system connectors and APIs | Business Analyst + IT |
| Unit Testing | Test individual components | Business Analyst |
| End-to-End Testing | Full process testing | Business Analyst |
| Documentation | Bot specification, runbook | Business Analyst |
| UAT Preparation | Prepare for business testing | Digital Product Owner + Business |

### 7.3 Ongoing Governance During Build

| Control | Frequency | Owner |
| --- | --- | --- |
| Sprint Reviews | Every sprint | Digital Product Owner |
| Code/Bot Review Approval | Every merge/release | Head of AI Engineering |
| Standards Compliance Check | Weekly | Head of AI Engineering |
| Progress Reporting | Bi-weekly | Head of AI Engineering |
| Risk Issue Escalation | As needed | Data Scientist / Business Analyst |
| IT Coordination Check | Weekly | Head of AI Engineering |

### 7.4 Required Artifacts (Produced During Build)

| Artifact | Description |
| --- | --- |
| Model Card | Comprehensive model documentation |
| Training Data Documentation | Data sources, transformations, quality |
| Feature Documentation | Feature definitions and engineering |
| Test Results | Unit, integration, performance test results |
| Code Repository | Version-controlled, reviewed code |
| Model Artifacts | Trained model, serialized artifacts |
| Deployment Package | Containerized, deployable package |

──────────────────────────────────────────────────

## 8. Gate 3: Validation Approval

### 8.1 Entry Criteria

Build phase complete

All build artifacts delivered

Model ready for validation

### 8.2 Validation Phase Activities

| Activity | Description | Owner |
| --- | --- | --- |
| Independent/Peer Validation | Model validation per standards | Validator (per tier) |
| Business UAT | Business acceptance testing | Business Team |
| Security Testing | Penetration testing, vulnerability scan | InfoSec |
| Performance Testing | Load testing, latency validation | MLOps Engineer |
| Compliance Review | Regulatory compliance check | Compliance |
| Operational Readiness | Confirm ops team readiness | MLOps Engineer |

### 8.3 Validation Approach by Tier

| Tier | Validation Type | Validator | Scope |
| --- | --- | --- | --- |
| Tier 1 | Independent Validation | External or dedicated MRM (when established) | Comprehensive |
| Tier 2 | Peer Validation | Different AI Engineering team member | Standard |
| Tier 3 | Self-Validation with Review | Developer + Lead review | Abbreviated |

### 8.4 Validation Scope

| Validation Area | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- |
| Conceptual Soundness | Comprehensive | Standard | Brief |
| Data Quality | Comprehensive | Standard | Checklist |
| Model Performance | Comprehensive | Standard | Standard |
| Fairness and Bias | Comprehensive | Standard | Checklist |
| Implementation Verification | Comprehensive | Standard | Code review |
| Sensitivity Analysis | Required | Recommended | Optional |
| Stress Testing | Required | Recommended | Optional |
| Challenger Analysis | Required | Optional | - |

### 8.5 GenAI-Specific Validation

| Validation Area | Description |
| --- | --- |
| Output Quality | Accuracy, relevance, coherence assessment |
| Hallucination Testing | Factual accuracy validation |
| Prompt Injection Testing | Security testing for prompt attacks |
| Guardrail Effectiveness | Validate content filtering |
| RAG Retrieval Quality | Validate retrieval accuracy (if applicable) |
| Edge Case Testing | Unusual input handling |

### 8.6 Agentic AI-Specific Validation

| Validation Area | Description |
| --- | --- |
| Boundary Testing | Validate action limits are enforced |
| Tool Access Testing | Verify appropriate API permissions |
| Override Testing | Validate human intervention works |
| Cascade Testing | Test multi-step action chains |
| Failure Mode Testing | Validate graceful degradation |
| Audit Trail Verification | Confirm all actions logged |

### 8.7 Required Artifacts

| Artifact | Description | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- | --- |
| Validation Report | Comprehensive validation findings | Full | Standard | Self-assessment |
| UAT Sign-off | Business acceptance confirmation | ✓ | ✓ | ✓ |
| Security Test Results | Penetration test and scan results | Full | Standard | Scan only |
| Performance Test Results | Load and latency test results | ✓ | ✓ | ✓ |
| Compliance Checklist | Regulatory compliance confirmation | ✓ | ✓ | Checklist |
| Findings Log | All findings and remediation status | ✓ | ✓ | ✓ |
| Operational Readiness Checklist | Ops team confirmation | ✓ | ✓ | ✓ |

### 8.8 Findings Classification

| Classification | Definition | Remediation Requirement |
| --- | --- | --- |
| Critical | Fundamental flaw; model cannot be deployed | Must remediate before Gate 3 approval |
| Major | Significant issue; material risk | Must remediate or accept with mitigation |
| Minor | Limited impact; improvement opportunity | Remediate post-deployment or accept |
| Observation | Best practice recommendation | Optional |

### 8.9 Exit Criteria / Gate Checklist

| Criterion | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- |
| Validation report complete | ✓ | ✓ | ✓ |
| No open Critical findings | ✓ | ✓ | ✓ |
| No open Major findings (or accepted) | ✓ | ✓ | ✓ |
| UAT sign-off received | ✓ | ✓ | ✓ |
| Security testing passed | ✓ | ✓ | ✓ |
| Performance requirements met | ✓ | ✓ | ✓ |
| Compliance review complete | ✓ | ✓ | Checklist |
| Model card finalized | ✓ | ✓ | ✓ |
| Monitoring configured | ✓ | ✓ | ✓ |
| Operational readiness confirmed | ✓ | ✓ | ✓ |
| Independent validation sign-off | ✓ | - | - |

### 8.10 Approval Authority

Tier 1: AI Steering Committee + Independent Validator

Tier 2: AI Engineering Lead + Peer Validator

Tier 3: AI Engineering Lead

### 8.11 Outcomes

Approved: Proceed to Production Deployment

Conditional Approval: Proceed with specific conditions (e.g., enhanced monitoring)

Remediate: Address findings and re-present

Rejected: Validation failures prevent deployment; return to Build or archive

──────────────────────────────────────────────────

## 9. Gate 4: Production Approval

### 9.1 Entry Criteria

Gate 3 approval received

Deployment preparation complete

Production environment ready

### 9.2 Pre-Production Activities

| Activity | Description | Owner |
| --- | --- | --- |
| Deployment Runbook Preparation | Finalize deployment procedures | MLOps Engineer |
| Rollback Plan | Document rollback procedures | MLOps Engineer |
| Production Environment Verification | Confirm production readiness | MLOps Engineer |
| Change Management | Submit change request | MLOps Engineer |
| Communication Plan | Stakeholder communication | Product Owner |
| Hypercare Plan | Post-deployment support plan | AI Engineering |
| Go-Live Checklist | Final pre-deployment checklist | MLOps Engineer |

### 9.3 Deployment Approach Options

| Approach | Description | When to Use |
| --- | --- | --- |
| Blue-Green | Full switch between environments | Standard approach |
| Canary | Gradual traffic shift | Risk mitigation |
| Shadow | Parallel run without impact | High-risk models |
| A/B Test | Controlled experiment | Business optimization |

### 9.4 Required Artifacts

| Artifact | Description | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- | --- |
| Deployment Runbook | Step-by-step deployment procedures | Comprehensive | Standard | Abbreviated |
| Rollback Plan | Rollback procedures and triggers | ✓ | ✓ | ✓ |
| Change Request | Approved change ticket | ✓ | ✓ | ✓ |
| Go-Live Checklist | Pre-deployment verification | ✓ | ✓ | ✓ |
| Communication Plan | Stakeholder notifications | ✓ | ✓ | Simplified |
| Hypercare Plan | Post-deployment support | ✓ | ✓ | Simplified |
| Monitoring Dashboard | Production monitoring ready | ✓ | ✓ | ✓ |

### 9.5 Exit Criteria / Gate Checklist

| Criterion | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- |
| Gate 3 approval confirmed | ✓ | ✓ | ✓ |
| Deployment runbook reviewed | ✓ | ✓ | ✓ |
| Rollback plan tested | ✓ | ✓ | - |
| Change request approved | ✓ | ✓ | ✓ |
| Production environment verified | ✓ | ✓ | ✓ |
| Monitoring dashboard active | ✓ | ✓ | ✓ |
| Support team briefed | ✓ | ✓ | ✓ |
| Business sponsor go-live approval | ✓ | ✓ | ✓ |
| Risk/Compliance final sign-off | ✓ | ✓ | - |

### 9.6 Approval Authority

Tier 1: AI Steering Committee

Tier 2: AI Engineering Lead

Tier 3: AI Engineering Lead (may delegate)

### 9.7 Outcomes

Go: Proceed with production deployment

Conditional Go: Proceed with specific conditions (e.g., limited rollout)

No-Go: Deployment blocked; address concerns

──────────────────────────────────────────────────

## 10. Gate 5: Post-Implementation Review (PIR)

### 10.1 Entry Criteria

Production deployment complete

Hypercare period complete (typically 2-4 weeks)

Initial production data available

### 10.2 PIR Activities

| Activity | Description | Owner |
| --- | --- | --- |
| Deployment Assessment | Assess deployment execution | MLOps Engineer |
| Performance Assessment | Assess model performance in production | ML Engineer |
| Business Outcome Assessment | Assess against success metrics | Business Sponsor |
| Issue Review | Review incidents and issues during deployment | AI Engineering |
| Lessons Learned | Document learnings and improvements | AI Engineering Lead |
| Handover to Operations | Formal transition to BAU | MLOps Engineer |

### 10.3 Required Artifacts

| Artifact | Description | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- | --- |
| PIR Report | Post-implementation review findings | Comprehensive | Standard | Brief |
| Production Performance Report | Initial production metrics | ✓ | ✓ | ✓ |
| Business Outcome Report | Progress against success metrics | ✓ | ✓ | ✓ |
| Incident Log | Deployment incidents and resolutions | ✓ | ✓ | If applicable |
| Lessons Learned | Documented learnings | ✓ | ✓ | ✓ |
| Updated Model Inventory | Registry entry updated | ✓ | ✓ | ✓ |

### 10.4 Exit Criteria / Gate Checklist

| Criterion | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- |
| PIR report complete | ✓ | ✓ | ✓ |
| Production performance acceptable | ✓ | ✓ | ✓ |
| No critical open issues | ✓ | ✓ | ✓ |
| Monitoring operating effectively | ✓ | ✓ | ✓ |
| Model Inventory updated | ✓ | ✓ | ✓ |
| Operations team handover complete | ✓ | ✓ | ✓ |
| Lessons learned documented | ✓ | ✓ | ✓ |
| Next review date scheduled | ✓ | ✓ | ✓ |

### 10.5 Approval Authority

Tier 1: AI Steering Committee

Tier 2: AI Engineering Lead

Tier 3: AI Engineering Lead

### 10.6 Outcomes

Closed - Successful: Deployment successful; transition to BAU

Closed - With Actions: Successful with follow-up actions required

Extended Hypercare: Extended support period required

Rollback: Production issues require rollback

──────────────────────────────────────────────────

## 11. Ongoing Operations Governance

### 11.1 Monitoring Requirements

| Monitoring Type | Frequency | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- | --- |
| Technical Metrics (latency, availability) | Real-time | ✓ | ✓ | ✓ |
| Data Drift Monitoring | Daily/Weekly | Daily | Weekly | Weekly |
| Model Performance Metrics | Daily/Weekly | Daily | Weekly | Weekly |
| Business Metrics | Weekly/Monthly | Weekly | Weekly | Monthly |
| Alert Review | As triggered | Immediate | <4 hours | <24 hours |

### 11.2 Periodic Review Schedule

| Review Type | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- |
| Performance Review | Quarterly | Semi-annual | Annual |
| Full Revalidation | Annual | Biennial | Triennial |
| Business Value Review | Annual | Annual | Annual |

### 11.3 Retraining Governance

| Change Type | Gate Requirement | Approval Authority |
| --- | --- | --- |
| Scheduled retrain (no changes) | Streamlined Gate 3-4 | AI Eng Lead |
| Retrain with parameter tuning | Gate 3-4 | AI Eng Lead |
| Feature changes | Gate 2-4 | AI Eng Lead (Tier 2: Steering Committee) |
| Algorithm/approach change | Full gates (1-5) | Per tier |
| Emergency retrain | Expedited Gate 3-4 with post-hoc review | AI Eng Lead |

### 11.4 Trigger Events for Model Review

| Trigger | Action | Timeline |
| --- | --- | --- |
| Performance drift beyond threshold | Initiate review | Within 5 days |
| Data drift beyond threshold | Assess impact | Within 5 days |
| Business metric degradation | Initiate review | Within 10 days |
| Regulatory change | Assess impact | Within 30 days |
| Security vulnerability | Immediate assessment | Within 24 hours |
| Upstream data source change | Assess impact | Within 10 days |
| Customer complaint | Investigate | Within 5 days |

──────────────────────────────────────────────────

## 12. Model Retirement Governance

### 12.1 Retirement Triggers

Business use case no longer valid

Replaced by superior model

Regulatory or compliance requirement

Technical obsolescence

Cost-benefit no longer favorable

### 12.2 Retirement Process

| Step | Activity | Owner |
| --- | --- | --- |
| 1 | Retirement proposal submitted | Business Sponsor or AI Eng |
| 2 | Impact assessment | AI Engineering |
| 3 | Stakeholder communication | Product Owner |
| 4 | Retirement plan development | MLOps Engineer |
| 5 | Approval | AI Eng Lead (Tier 1: Steering Committee) |
| 6 | Retirement execution | MLOps Engineer |
| 7 | Archive and documentation | AI Engineering |
| 8 | Model Inventory update | AI Engineering |

### 12.3 Retirement Checklist

| Item | Required |
| --- | --- |
| Downstream consumers notified | ✓ |
| Alternative solution in place (if needed) | ✓ |
| Data retention requirements addressed | ✓ |
| Model artifacts archived | ✓ |
| Documentation archived | ✓ |
| Model Inventory updated | ✓ |
| Monitoring decommissioned | ✓ |
| Infrastructure deprovisioned | ✓ |

──────────────────────────────────────────────────

## 13. Exception Handling

### 13.1 Exception Types

| Exception Type | Description | Approval Authority |
| --- | --- | --- |
| Gate bypass | Skip or combine gates | AI Steering Committee |
| Accelerated timeline | Compressed gate timelines | AI Engineering Lead |
| Documentation waiver | Reduced documentation requirements | AI Engineering Lead |
| Validation scope reduction | Reduced validation scope | AI Engineering Lead + Risk |
| Non-standard architecture | Deviation from approved patterns | AI Steering Committee |
| Emergency deployment | Critical fix outside normal process | AI Engineering Lead + post-hoc review |

### 13.2 Exception Request Process

| Step | Activity | Timeline |
| --- | --- | --- |
| 1 | Exception request submitted with justification | - |
| 2 | Risk assessment of exception | 2 days |
| 3 | Approval decision | 3 days |
| 4 | Mitigating controls documented | Before implementation |
| 5 | Exception log updated | Immediately |
| 6 | Post-hoc review (if applicable) | Within 30 days |

### 13.3 Exception Documentation

| Field | Description |
| --- | --- |
| Exception ID | Unique identifier |
| Use Case | Related use case |
| Exception Type | Type of exception |
| Justification | Business and risk justification |
| Mitigating Controls | Compensating controls |
| Approval | Approver and date |
| Expiry | Validity period |
| Review Date | Post-hoc review date |

──────────────────────────────────────────────────

## 14. RACI Matrix

### 14.1 Stage-Gate RACI

| Activity | Business Sponsor | AI Eng Lead | ML Engineer | MLOps | Solutions Arch | Risk/Compliance | AI Steering |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Gate 0: Intake |  |  |  |  |  |  |  |
| Submit use case | A | C | - | - | - | C | I |
| Screening | C | A | R | - | C | C | I (Tier 1) |
| Approval decision | C | A/R | - | - | - | C | A (Tier 1) |
| Gate 1: Feasibility |  |  |  |  |  |  |  |
| Discovery activities | C | A | R | R | R | C | - |
| Feasibility assessment | C | A | R | - | R | C | - |
| Approval decision | C | A | R | - | C | C | - |
| Gate 2: Design |  |  |  |  |  |  |  |
| Solution design | C | A | R | R | R | C | - |
| Architecture review | I | A | R | R | R | C | - |
| Approval decision | C | A/R | - | - | R | C | A (Tier 1) |
| Build Phase |  |  |  |  |  |  |  |
| Model development | I | A | R | R | C | - | - |
| Code review | - | A | R | R | - | - | - |
| Gate 3: Validation |  |  |  |  |  |  |  |
| Validation activities | C | A | R | R | - | C | - |
| UAT | A | C | R | - | - | - | - |
| Approval decision | C | A/R | - | - | - | C | A (Tier 1) |
| Gate 4: Production |  |  |  |  |  |  |  |
| Deployment prep | I | A | R | R | - | - | - |
| Go-live decision | A | A/R | - | R | - | C | A (Tier 1) |
| Gate 5: PIR |  |  |  |  |  |  |  |
| PIR assessment | C | A | R | R | - | C | I |
| Closure decision | C | A | R | - | - | C | I (Tier 1) |

Legend: R = Responsible, A = Accountable, C = Consulted, I = Informed

──────────────────────────────────────────────────

## 15. Templates

### 15.1 Template Inventory

| Template | Purpose | Location |
| --- | --- | --- |
| Gate Review Checklist | Checklist for each gate | Appendix A |
| Stage Completion Certificate | Formal gate approval | Appendix B |
| Exception Request Form | Request for exception | Appendix C |
| Retraining Gate Checklist | Streamlined retrain gates | Appendix D |
| Retirement Checklist | Model retirement | Appendix E |

──────────────────────────────────────────────────

## Appendix A: Gate Review Checklists

### A.1 Gate 0 Checklist

[Detailed checklist items]

### A.2 Gate 1 Checklist

[Detailed checklist items]

### A.3 Gate 2 Checklist

[Detailed checklist items]

### A.4 Gate 3 Checklist

[Detailed checklist items]

### A.5 Gate 4 Checklist

[Detailed checklist items]

### A.6 Gate 5 Checklist

[Detailed checklist items]

──────────────────────────────────────────────────

## Appendix B: Stage Completion Certificate Template

| Field | Value |
| --- | --- |
| Use Case ID |  |
| Use Case Name |  |
| Gate |  |
| Gate Date |  |
| Decision | Approved / Approved with Conditions / Not Approved |
| Conditions (if applicable) |  |
| Approver |  |
| Signature |  |
| Next Gate Target |  |

──────────────────────────────────────────────────

## Appendix C: Exception Request Form

[Detailed exception request form]

──────────────────────────────────────────────────

## Document Control

### Related Documents

AI, Automation & Intelligent Solutions Governance Operating Model (AI-GOV-001)

AI, Automation & Intelligent Solutions Intake & Prioritization Framework (AI-GOV-002)

AI, Automation & Intelligent Solutions Inventory Register (AI-GOV-004)

Compliance Traceability Matrix (AI-GOV-CTM)

AI/ML Development Standards (AI-ENG-001)

Automation Development Standards (AI-ENG-002)

Model Validation Standards (AI-VAL-001)

### Approval History

| Version | Date | Author | Approver | Changes |
| --- | --- | --- | --- | --- |
| 1.0 | [Date] | [Author] | [Approver] | Initial release |
| 1.1 | [Date] | [Author] | [Approver] | Added Automation scope; Updated org structure; IT coordination |